## Sheet2
Si No	Modules	Task	Hours	Plan
1	Review / Star Rating	1: Star rating Default available	16	Starting Date	Ending Date
		2: Customer can able to post review about the product		11/05/15	16/05/2015	R1
		3: Admin need to approve the review in back en

2	Image / Video Display	Can able to upload multiple image
		Can able to upload videos	8	11/05/15	13/05/2015	R2

	Abandoned Cart	Abandoned Cart

	Product	Product Comparison
		Video Tutorial and Product catalog	8	13/05/2015	16/05/2015	R2
		Display Daily Deals / Admin can able to create daily deals	8	18/05/2015	19/05/2015	R2
		Customized gifts option to customize the produt	24	18/05/2015	23/05/15	R1
		Product Catelog – Grid View.
		Recommended Products.
		New Arrival
		Best Deals
		Discount and Offers.	4	20/05/2015	20/05/2015	R2
		Multivender	40	06-062015	20-06-2015	R1

	Revards / Points	Loyalty Program	8	21/05/2015	23/05/2015	R2
		User can purchase using the points	8	25/05/2015	26/05/2015	R1
		Coupens	2	27/05/2015	28/05/2015	R1
	Shipping
		Can able to track the shipping
		Can able to calculate aprox delivery time
	Payment
		Shopping site to support multiple country / currency
		`pg integration	16

	Search
		Search Functionality (Most Critical)

	Cart
		5 Click Checkout Process (Most Critical)	20	25/05/2015	30/05/2015	R2

	Ordering
		Order Confirmation – SMS Notification / Email	12	29/05/2015	30/05/2015	R1

	Reporting
		Customzed Report based on admin side	40

	Customer
		Feedback	4	02/06/15	03/06/15	R1

	General
		Multilanguage storefront

	Newsletter
		Newsletter – Singup / Create / send	8	02/06/15	05/06/15	R1

		Testing / Bug fixing		15/05/2015	30/06/2015
		Product Entry		01/07/15	15/07/2015

		Lanch		15/7/2015

## Sheet1
Tasks List	Remarks	Time
Review and Star ratings	It's possible	1 day
Size and dimensions	It's possible	1 day
Pictures & Videos for Product display	we have to develop or find any plugin for demonstrate video
Abandoned Cart	It's possible	1 day
Daily Deals	Need the plugin
Product Comparison	It's possible	1 day
Loyalty Program	This can be handled at a later stage.
Multilanguage storefront	This can be handled at a later stage.
Video Tutorials / Product Usage Tour: Video Tutorials / Product Usage Tour:	It's possible	1 day
Customized Gifts Customized Gifts	Need the plugin	2 day
Shopping site to support multiple country / currency	This can be handled at a later stage.
Product Catelog – Grid View.Product Catelog – Grid View.	It's possible	1 day
New Arrival	It's possible	1 day
Recommended Products.	This can be handled at a later stage.
Admin – Product enrollment with categories, Product Tracking and Shipping	It's possible	2 day
Payment Gateway Integration	It's possible	1 day
Discount and Offers.	It's possible	1 day
Search Functionality (Most Critical)	It's possible	1 day
5 Click Checkout Process (Most Critical)	It's possible	1 day
Order Confirmation – SMS Notification	This can be handled at a later stage.
Shipping Duration	It's possible	1 day
Best Deals	Need the plugin	2 day
Reporting	It's possible	1 day
Feedback	It's possible	1 day
	Total days	20 days